# Quantitative Project Risk Analysis with PRA

Paul Govan (GE Aerospace, paul.govan2@gmail.com)

2026-07-13

Abstract

The PRA package for R is the first package of its kind to unify a core set of widely adopted quantitative project risk analysis methods in a single, open-source, Comprehensive R Archive Network (CRAN)-available implementation: the Second Moment Method (SMM), Monte Carlo simulation (MCS), earned value management (EVM), contingency and sensitivity analysis, Bayesian risk inference and updating, sigmoidal learning curves, and design structure matrices (DSM). Beyond this foundational core, PRA makes two further contributions. As a secondary contribution, version 0.5.0 provides the first software implementation of the experimental causal- and probabilistic-network methods for project risk, supporting forward simulation of cost uncertainty and Bayesian conditioning along causal chains. As a third contribution, it exposes every analytical function as a tool over the Model Context Protocol (MCP), paired with a documented set of Agent Skills, so that large-language-model agents can run project risk analyses directly. The package adheres to rOpenSci Statistical Software Review standards and is supported by a continuous-integration test suite running across macOS, Windows, and Ubuntu.

Keywords: project risk analysis, Monte Carlo simulation, earned value management, Bayesian inference, design structure matrix, R.

# 1	Introduction

Quantitative risk analysis is a foundational discipline in project management, enabling organizations to assess schedule and cost uncertainty, identify high-impact risk drivers, and set evidence-based contingency reserves. This article presents PRA, an open-source R package that unifies the core quantitative methods of project risk analysis—schedule and cost uncertainty, earned value management, sensitivity and contingency analysis, learning curves, and dependency structure analysis—under a single, reproducible, CRAN-validated API.

Despite broad industry adoption of quantitative methods, open-source tooling for integrated project risk analysis in R remains fragmented. Proprietary platforms such as Oracle Primavera Risk Analysis and Palisade @RISK provide integrated workflows but impose licensing costs and limit reproducibility. Within R, no single package unifies Monte Carlo schedule risk, earned value management, Bayesian risk inference, sigmoidal learning curves, and dependency structure analysis under a common API. The mc2d package (Pouillot and Delignette-Muller 2010) provides general-purpose two-dimensional Monte Carlo simulation but has no project-specific constructs. The sensitivity package (Iooss et al. 2024) implements variance-based indices for general functions but does not integrate with schedule or cost models. EVM metrics are absent from CRAN entirely. Bayesian packages such as rstan (Stan Development Team 2024) and brms (Bürkner 2017) operate at a high level of generality and require substantial expertise to apply in project risk contexts.

PRA makes three contributions. The primary contribution addresses the gap above directly: To the author’s knowledge, PRA is the first CRAN package to integrate these project risk analysis methods in a single API. The comparison (Table 1.1) is based on a review of general-purpose Monte Carlo and sensitivity packages and the dominant commercial platform, though a comprehensive survey of all R packages and domain-specific tools was not conducted.  Where the existing ecosystem is fragmented across general-purpose packages, none project-specific, PRA provides one reproducible, auditable API for the full workflow, integrating outputs across modules in a manner not available in the fragmented ecosystem. For example, MCS results feed directly into contingency and sensitivity analyses, and Bayesian risk updates can re-parameterize task distributions for subsequent simulations). The package targets project analysts who work in R and require outputs compatible with standard reporting pipelines. It adheres to rOpenSci Statistical Software Review (SRR) standards (rOpenSci Statistical Software Peer Review 2021) and uses minimal hard dependencies: mc2d (Pouillot and Delignette-Muller 2010) for triangular distribution families and minpack.lm (Elzhov et al. 2016) for nonlinear least squares fitting.

As a secondary contribution, PRA provides, the first open-source R implementation of the experimental causal- and probabilistic-network methods for project risk introduced by Govan (2014) and Govan and Damnjanovic (2016), who grounded causal networks in the resource-based view, demonstrating that organizational capabilities and shared resources, not just schedule uncertainty, are the structural pathways through which risks propagate across project tasks—and extended by Govan and Damnjanovic (2020) with structural network measures that quantify the topology of project risk networks. The experimental probabilistic network module (Section 6) operationalizes these ideas, propagating distributions through the causal chain from risks to total project cost.

As a third contribution, PRA is the first project risk analysis package, and to the author’s knowledge one of the first R packages in any domain, to expose its analytical methods as tools callable by LLM agents over the Model Context Protocol (MCP) and paired with a documented set of Agent Skills (Section 7). The optional MCP server activates through Suggests-only dependencies, so the analytical core carries no additional runtime cost.

The following table underscores the primary contribution: no existing R package or commercial platform covers the foundational project risk workflow that PRA unifies. It summarizes how PRA compares with the most closely related R packages and the dominant commercial platform.

Table 1.1: Comparison of PRA with the most closely related R packages (mc2d and sensitivity, identified via CRAN Task Views for Distributions and Design of Experiments) and the dominant commercial platform (@RISK). “Exp.” = experimental feature; “—” = not supported.

| Feature | PRA | mc2d | sensitivity | rstan/brms | @RISK |
| --- | --- | --- | --- | --- | --- |
| MCS schedule risk | Yes | Partial | — | — | Yes |
| EVM (11 metrics) | Yes | — | — | — | Yes |
| Bayesian updating | Yes | — | — | Yes | — |
| Sigmoidal learning curves | Yes | — | — | — | — |
| Design structure matrices | Yes | — | — | — | — |
| Probabilistic networks | Exp. | — | — | Yes | — |
| MCP tool server | Yes | — | — | — | — |
| Open-source (CRAN) | Yes | Yes | Yes | Yes | — |
| SRR-compliant | Yes | — | — | — | — |

The package is installed from CRAN in the standard way:

install.packages("PRA")
library("PRA")

Optional dependencies—ellmer (Wickham et al. 2025), mcptools, and jsonlite—are only required for the MCP server, pra_mcp_server().

The remainder of this article describes each analytical module in turn, with working code examples drawn from the same R session. Section 2 describes the design objectives of PRA. Section 3 covers schedule and cost uncertainty methods (SMM, MCS, contingency, sensitivity, and correlation matrix construction). Section 4 describes earned value management. Section 5 describes sigmoidal learning curves. Section 6 covers design structure matrices. Section 7 introduces the experimental probabilistic network module. Section 8 describes the Model Context Protocol integration. Section 9 presents an integrated case study. Section 10 concludes.

# 2	Schedule and Cost Uncertainty

Two complementary methods are provided for quantifying schedule and cost uncertainty: the Second Moment Method for rapid analytical estimates, and Monte Carlo simulation for full distributional analysis. Contingency extraction and sensitivity analysis complete the workflow.

We illustrate the workflow with building_project, a bundled example dataset describing a mid-rise commercial building with six work packages, adapted from the construction-project examples in Damnjanovic and Reinschmidt (2020).

data("building_project", package = "PRA")
bp <- building_project
bp$task_names

## [1] "Site Preparation & Earthworks"  "Foundations"                   
## [3] "Structural Frame"               "Building Envelope"             
## [5] "Mechanical/Electrical/Plumbing" "Interior Fit-out & Finishes"

## 2.1	Second Moment Method

The Second Moment Method (SMM) propagates task-level means and variances to project-level estimates using the Central Limit Theorem (Benjamin and Cornell 2000). For a project with n tasks:

E[X]=i=1nE[Xi], Var(X)=i=1nVar(Xi)+2i<j​ρijσiσj

The six task durations are triangular, so we obtain their means and variances in closed form and propagate them with smm():

tri_mean <- function(d) (d$a + d$b + d$c) / 3
tri_var  <- function(d) (d$a^2 + d$b^2 + d$c^2 -
                         d$a * d$b - d$a * d$c - d$b * d$c) / 18
task_means <- vapply(bp$task_distributions, tri_mean, numeric(1))
task_vars  <- vapply(bp$task_distributions, tri_var,  numeric(1))

result <- smm(task_means, task_vars)   # independent tasks
cat("Total mean:", round(result$total_mean, 2), "weeks\n")

## Total mean: 71.67 weeks

cat("Total SD:  ", round(result$total_std,  2), "weeks\n")

## Total SD:   4.53 weeks

Positive correlation between tasks inflates the total variance; smm() accepts a correlation matrix and adds the covariance terms analytically:

result_cor <- smm(task_means, task_vars, bp$cor_mat)
cat("Total SD (correlated):", round(result_cor$total_std, 2), "weeks\n")

## Total SD (correlated): 6.59 weeks

SMM is useful when only first and second moments are available and a rapid estimate is needed. When task distributions are non-normal or accurate tail behavior is required, Monte Carlo simulation is preferred.

## 2.2	Monte Carlo Simulation

mcs() propagates uncertainty through a project network by drawing samples from user-specified task distributions, triangular, normal, or uniform, over a large number of iterations (Vose 2008). By default the tasks are sampled independently, where an optional correlation matrix is supported, though its current handling is approximate (Section 9). The current implementation applies a Cholesky factor to induce correlation, which reproduces the target rank correlation but may distort the marginal means. See Section 9.1 for details and planned improvements.

set.seed(42)
results <- mcs(10000, bp$task_distributions)
cat("Simulated mean:", round(results$total_mean, 2), "weeks\n")

## Simulated mean: 71.72 weeks

cat("Simulated SD:  ", round(results$total_sd,   2), "weeks\n")

## Simulated SD:   4.57 weeks

The mcs() function returns an S3 object of class "mcs" with a print() method that summarizes percentiles. The full simulated distribution is available in results$total_distribution. On a modern laptop, 10,000 simulations of a six-task network complete in under one second; increasing the count to 100,000 provides more precise tail estimates at roughly ten-fold additional runtime. The default of 10,000 balances accuracy and speed for most practical analyses. Convergence diagnostics (for example, Monte Carlo standard error or batch-means analysis) are not provided, and users should verify that results stabilize as the iteration count increases for their specific use case, especially for tail percentiles.

### 2.2.1	Numerical Validation

For independent tasks, the Central Limit Theorem makes the SMM estimates the exact moments of the total, so the Monte Carlo simulation should reproduce them. The two agree to within Monte Carlo error, validating the sampling engine:

cat(sprintf("Mean:  SMM %.2f  vs  MCS %.2f\n",
            result$total_mean, results$total_mean))

## Mean:  SMM 71.67  vs  MCS 71.72

cat(sprintf("SD:    SMM %.2f  vs  MCS %.2f\n",
            result$total_std,  results$total_sd))

## SD:    SMM 4.53  vs  MCS 4.57

hist(results$total_distribution,
  breaks = 50, freq = FALSE,
  main = "MCS: Total Project Duration",
  xlab = "Duration (weeks)", col = "steelblue", border = "white"
)
lines(density(results$total_distribution), col = "tomato", lwd = 2)
abline(v = results$total_mean, lty = 2, lwd = 1.5)

Figure 2.1: Distribution of simulated total project durations. The dashed vertical line marks the mean.

## 2.3	Correlation Matrix Construction

Both smm() and mcs() accept a correlation matrix to model dependence between tasks. cor_matrix() constructs a valid positive-definite correlation matrix by empirically sampling from a set of task distributions, providing a convenient way to derive the correlation input from the same distributional assumptions used elsewhere in the workflow.

dists <- list(
  normal  = function(n) rnorm(n, mean = 10, sd = 2),
  triang  = function(n) mc2d::rpert(n, min = 5, mode = 10, max = 15),
  uniform = function(n) runif(n, min = 8, max = 12)
)
C_emp <- cor_matrix(num_samples = 1000, num_vars = 3, dists = dists)
print(round(C_emp, 3))

##        [,1]   [,2]   [,3]
## [1,]  1.000 -0.028 -0.022
## [2,] -0.028  1.000 -0.010
## [3,] -0.022 -0.010  1.000

## 2.4	Contingency Analysis

contingency() extracts a reserve buffer as the difference between a high-confidence percentile and the base (median) estimate, a standard approach in project risk practice (Project Management Institute 2021).

reserve <- contingency(results, phigh = 0.80, pbase = 0.50)
cat("Schedule contingency (P80 - P50):", round(reserve, 2), "weeks\n")

## Schedule contingency (P80 - P50): 3.98 weeks

## 2.5	Sensitivity Analysis

sensitivity() decomposes total project variance by task contribution, producing the inputs for a Tornado chart. Each task’s index is its own variance plus its covariance with every other task, expressed as a proportion of total project variance.

sens <- sensitivity(bp$task_distributions)
names(sens) <- paste0("T", seq_along(sens))
barplot(sort(sens),
  horiz = TRUE, col = "steelblue",
  main = "Sensitivity: Task Contributions",
  xlab = "Proportion of Total Variance"
)

Figure 2.2: Tornado chart: each bar shows a task’s share of total project duration variance.

Tasks with larger bars are the dominant drivers of total risk; mitigation resources should be directed there first.

# 3	Earned Value Management

The EVM module implements the complete ANSI/EIA-748 suite of eleven performance metrics (Fleming and Koppelman 2010). The three core quantities, Planned Value (PV), Earned Value (EV), and Actual Cost (AC), are computed first. All performance indices and forecasts follow from them.

bac         <- 500000                          # budget at completion ($)
schedule    <- c(0.10, 0.25, 0.50, 0.75, 1.00) # cumulative value curve
time_period <- 3

pv_val <- pv(bac, schedule, time_period)
ev_val <- ev(bac, actual_per_complete = 0.40)
ac_val <- ac(c(45000, 110000, 135000), time_period, cumulative = FALSE)

cat("PV: $", format(pv_val, big.mark = ","), "\n")

## PV: $ 250,000

cat("EV: $", format(ev_val, big.mark = ","), "\n")

## EV: $ 2e+05

cat("AC: $", format(ac_val, big.mark = ","), "\n")

## AC: $ 290,000

spi_val  <- spi(ev_val, pv_val)
cpi_val  <- cpi(ev_val, ac_val)
sv_val   <- sv(ev_val,  pv_val)
cv_val   <- cv(ev_val,  ac_val)

cat("SPI:", round(spi_val, 3), "  CPI:", round(cpi_val, 3), "\n")

## SPI: 0.8   CPI: 0.69

cat("SV: $", format(round(sv_val), big.mark = ","),
    "  CV: $", format(round(cv_val), big.mark = ","), "\n")

## SV: $ -50,000   CV: $ -90,000

Both SPI <1 and CPI <1 indicate the project is behind schedule and over budget. The eac() function provides three completion forecasts under different efficiency assumptions:

cat("EAC (typical):  $", format(round(eac(bac, method = "typical",
    cpi = cpi_val)), big.mark = ","), "\n")

## EAC (typical):  $ 725,000

cat("EAC (atypical): $", format(round(eac(bac, method = "atypical",
    ac = ac_val, ev = ev_val)), big.mark = ","), "\n")

## EAC (atypical): $ 590,000

cat("EAC (combined): $", format(round(eac(bac, method = "combined",
    cpi = cpi_val, ac = ac_val, ev = ev_val, spi = spi_val)),
    big.mark = ","), "\n")

## EAC (combined): $ 833,750

The remaining EVM metrics are:

eac_typ <- eac(bac, method = "typical", cpi = cpi_val)
cat("ETC:  $", format(round(etc(bac, ev_val, cpi = cpi_val)), big.mark = ","), "\n")

## ETC:  $ 435,000

cat("TCPI:", round(tcpi(bac, ev_val, ac_val), 3), "\n")

## TCPI: 1.429

cat("VAC:  $", format(round(vac(bac, eac_typ)), big.mark = ","), "\n")

## VAC:  $ -225,000

The To-Complete Performance Index (TCPI) reports the cost efficiency required on all remaining work to finish within the original budget; values substantially above 1.0 signal an unrealistic recovery target.

# 4	Learning Curves

Sigmoidal (S-curve) models capture the characteristic pattern of project progress: slow start, rapid acceleration, and plateau approaching 100% completion. PRA provides three model types, Logistic, Pearl, and Gompertz, fitted via the Levenberg–Marquardt nonlinear least-squares algorithm in minpack.lm (Elzhov et al. 2016).

progress <- data.frame(
  time       = 1:9,
  completion = c(5, 15, 40, 60, 70, 75, 80, 85, 90)
)

fit_log  <- fit_sigmoidal(progress, "time", "completion", "logistic")
fit_gomp <- fit_sigmoidal(progress, "time", "completion", "gompertz")

cat("Logistic RSE: ", round(summary(fit_log)$sigma,  2), "\n")

## Logistic RSE:  4.15

cat("Gompertz RSE: ", round(summary(fit_gomp)$sigma, 2), "\n")

## Gompertz RSE:  2.89

plot_sigmoidal(fit_log, progress, "time", "completion", "logistic",
               conf_level = 0.95,
               main = "Logistic Learning Curve",
               xlab = "Week", ylab = "Completion (%)")

Figure 4.1: Logistic learning curve with 95% confidence band. The shaded region widens as extrapolation extends beyond the observed data range.

predict_sigmoidal() generates forecasts with confidence bounds at arbitrary future time points:

preds <- predict_sigmoidal(fit_log, seq(10, 12, by = 0.5),
                            "logistic", conf_level = 0.95)
print(round(preds, 1))

##      x pred  lwr  upr
## 1 10.0 84.3 78.2 90.3
## 2 10.5 84.3 78.2 90.4
## 3 11.0 84.3 78.2 90.4
## 4 11.5 84.3 78.2 90.5
## 5 12.0 84.3 78.2 90.5

# 5	Dependency Structure Analysis

Building on Govan and Damnjanovic (2016, 2020) and the foundational DSM literature (Steward 1981; Browning 2001), the DSM module quantifies structural coupling between project tasks through shared resources and risks.

## 5.1	Design Structure Matrices

The Parent DSM is derived from the Resource–Task matrix S (rows = resources, columns = tasks) as P=S⊤S. Off-diagonal entry Pjk counts the number of resources shared between tasks j and k—the structural pathway through which disruptions propagate (Govan and Damnjanovic 2016).

S <- matrix(c(
  1, 0, 1, 0,
  1, 1, 0, 0,
  0, 1, 0, 1,
  0, 0, 1, 1,
  0, 1, 1, 0
), nrow = 4, ncol = 5)
rownames(S) <- paste0("R", 1:4)
colnames(S) <- paste0("T", 1:5)

p <- parent_dsm(S)
plot(p)

Figure 5.1: Parent DSM heatmap. Darker cells indicate more shared resources and stronger coupling between task pairs.

The Grandparent DSM adds a risk layer via the Risk–Resource matrix R, tracing dependencies from risks through resources to tasks. Off-diagonal entry Gjk counts the number of risks shared between task j and task k through the resource chain—a direct operationalization of the structural network measures developed in Govan and Damnjanovic (2020).

R_mat <- matrix(c(
  1, 0, 1,
  1, 1, 0,
  0, 1, 0,
  0, 0, 1
), nrow = 3, ncol = 4)
rownames(R_mat) <- paste0("Risk", 1:3)
colnames(R_mat) <- paste0("R", 1:4)

g <- grandparent_dsm(S, R_mat)
plot(g)

Figure 5.2: Grandparent DSM heatmap. Shows risk-based coupling: task pairs that share risk exposure through common resources tend to fail together.

Task pairs with high off-diagonal values in the Grandparent DSM represent concentrated risk exposure; these pairs are prime candidates for contingency buffering or resource decoupling.

# 6	Probabilistic Networks

Experimental. This module is the secondary contribution of PRA: an initial software implementation of the experimental causal-network methods; numerical validation against analytical benchmarks or alternative Bayesian network software is planned for future work (see Section 9.1). The probabilistic network module extends DSM structural analysis by attaching probability distributions to each node, enabling forward simulation of cost uncertainty and Bayesian conditioning on observed evidence. A probabilistic network is a directed acyclic graph in which nodes represent project variables (risks, resources, tasks, and the project total) and edges encode conditional dependencies (Pearl 2009; Govan 2014). Where a DSM counts shared resources between task pairs, a probabilistic network propagates distributions through the causal chain from risks to total project cost.

## 6.1	Building a Network

prob_net() constructs the network from a node data frame, a links data frame, and a named list of distributions. Distributions may be normal, lognormal, uniform, discrete, or conditional (switching between two sub-distributions depending on a discrete parent node); aggregate nodes sum their parents.

nodes <- data.frame(
  id = c("A","B","C","D","E","F","G","H","I"),
  label = c("Risk-1","Risk-2","Resource-1","Resource-2","Resource-3",
            "Task-1","Task-2","Task-3","Project"),
  stringsAsFactors = FALSE
)
links <- data.frame(
  source = c("A","B","C","D","E","F","G","H"),
  target = c("C","D","F","G","H","I","I","I"),
  stringsAsFactors = FALSE
)
distributions <- list(
  A = list(type = "discrete", values = c(1, 0), probs = c(0.70, 0.30)),
  B = list(type = "discrete", values = c(1, 0), probs = c(0.60, 0.40)),
  C = list(type = "conditional", condition = "A",
    true_dist  = list(type = "normal", mean = 30000, sd = 8000),
    false_dist = list(type = "normal", mean = 15000, sd = 3000)),
  D = list(type = "conditional", condition = "B",
    true_dist  = list(type = "normal", mean = 80000, sd = 20000),
    false_dist = list(type = "normal", mean = 50000, sd = 10000)),
  E = list(type = "normal", mean = 20000, sd = 4000),
  F = list(type = "aggregate", nodes = "C"),
  G = list(type = "aggregate", nodes = "D"),
  H = list(type = "aggregate", nodes = "E"),
  I = list(type = "aggregate", nodes = c("F","G","H"))
)
net <- prob_net(nodes, links, distributions = distributions)

## 6.2	Forward Simulation

prob_net_sim() draws samples from every node in topological order and returns a data frame with one column per node.

sim_net <- prob_net_sim(net, num_samples = 10000)
cat("Mean project cost: $", format(round(mean(sim_net$I)), big.mark = ","), "\n")

## Mean project cost: $ 113,612

cat("P80 project cost:  $", format(round(quantile(sim_net$I, 0.80)),
    big.mark = ","), "\n")

## P80 project cost:  $ 135,543

## 6.3	Learning: Conditioning on Evidence

prob_net_learn() clamps observed nodes to fixed values and re-simulates the downstream distribution, an observational update in the sense of Pearl (2009). The following call fixes Risk-2 (node B) to absent (value 0), ruling out Technical Complexity as a concern:

learn_net <- prob_net_learn(net, observations = list(B = 0),
                            num_samples = 10000)

prior_net_dens <- density(sim_net$I)
post_net_dens  <- density(learn_net$I)

plot(prior_net_dens, col = "steelblue", lwd = 2,
     main = "Total Project Cost: Prior vs. Posterior",
     xlab = "Cost ($)",
     xlim = range(c(sim_net$I, learn_net$I)),
     ylim = range(c(prior_net_dens$y, post_net_dens$y)))
lines(post_net_dens, col = "tomato", lwd = 2)
legend("topright",
  legend = c("Prior (Risk-2 uncertain)", "Posterior (Risk-2 = 0)"),
  col = c("steelblue", "tomato"), lwd = 2, bty = "n")

Figure 6.1: Total project cost before and after observing that Risk-2 (Technical Complexity) did not occur. Conditioning on Risk-2 = 0 eliminates the heavy upper tail and shifts the distribution leftward by roughly $30,000 in expectation.

## 6.4	Intervention: The do-Operator

Conditioning answers “what if we observe that a risk did not occur.” A distinct question is “what if we act to eliminate it.” prob_net_update() performs structural surgery on the network—adding or removing edges and replacing node distributions—which corresponds to the do-operator in Pearl’s causal calculus (Pearl 2009), as opposed to prob_net_learn(), which conditions without altering the graph. Suppose management funds a mitigation that decouples Resource-2 from Risk-2: remove the Risk-2 → Resource-2 edge and fix Resource-2 to its baseline cost.

inter_net <- prob_net_update(net,
  remove_links = data.frame(source = "B", target = "D"),
  update_distributions = list(
    D = list(type = "normal", mean = 50000, sd = 10000)
  )
)
do_net <- prob_net_sim(inter_net, num_samples = 10000)

cat("Prior mean:            $", format(round(mean(sim_net$I)),   big.mark = ","), "\n")

## Prior mean:            $ 113,612

cat("Seeing (Risk-2 = 0):   $", format(round(mean(learn_net$I)), big.mark = ","), "\n")

## Seeing (Risk-2 = 0):   $ 95,729

cat("Doing  (do(Risk-2=0)): $", format(round(mean(do_net$I)),    big.mark = ","), "\n")

## Doing  (do(Risk-2=0)): $ 95,625

Here seeing (prob_net_learn()) and doing (prob_net_update()) coincide because Risk-2 is an independent root cause with no shared upstream confounder, so conditioning on it and intervening on it induce the same downstream distribution. The two diverge when risks share a common cause—intervening severs the upstream pathway while observing propagates back through it—which is where the do-operator becomes indispensable.

## 6.5	Ranking Risks by Intervention

Repeating the intervention for each root risk and measuring the reduction in project-cost variance yields a principled, network-level mitigation ranking—a causal analog of the Tornado chart of Section 2:

base_var <- var(sim_net$I)

do_A <- prob_net_sim(prob_net_update(net,
  remove_links = data.frame(source = "A", target = "C"),
  update_distributions = list(C = list(type = "normal", mean = 15000, sd = 3000))),
  num_samples = 10000)

importance <- c(
  "Risk-1" = base_var - var(do_A$I),
  "Risk-2" = base_var - var(do_net$I)
)
barplot(sort(importance), horiz = TRUE, col = "steelblue",
  main = "Risk Importance: Variance Eliminated by do(risk = 0)",
  xlab = "Reduction in Project-Cost Variance")

Figure 6.2: Risk importance for the probabilistic network: the reduction in total project-cost variance achieved by intervening to eliminate each root risk. Taller bars indicate higher-priority mitigation targets.

The probabilistic network API is marked experimental and may evolve in future releases.

# 7	Model Context Protocol Integration

Version 0.5.0 of PRA exposes all analytical functions as tools callable by large-language-model (LLM) agents through the Model Context Protocol (MCP) (Anthropic 2024). pra_mcp_server() starts a server that advertises each tool—Monte Carlo simulation, EVM, Bayesian risk, learning curves, DSM, and the rest, so that Claude, Claude Code, and other MCP-compatible clients can invoke them as native tools. The server is registered in Claude Code with a single shell command:

claude mcp add -s project pra -- Rscript -e "PRA::pra_mcp_server()"

For Claude Desktop, add the following block to the MCP configuration file:

{
  "mcpServers": {
    "pra": { "command": "Rscript",
             "args": ["-e", "PRA::pra_mcp_server()"] }
  }
}

The tool definitions are built once with ellmer::tool() (Wickham et al. 2025) and served by mcptools. Each tool validates its JSON inputs and returns a plain-text summary for the LLM together with, where applicable, a rich HTML result with inline plots for clients that render it.

To help an agent decide when and how to call each tool, PRA bundles a set of Agent Skills under system.file("skills", package = "PRA"). Each skill is a SKILL.md file with structured guidance, when to use the method, which tool to call, the JSON argument format, and how to interpret the result, covering Monte Carlo simulation, sensitivity and contingency, EVM, Bayesian risk, learning curves, and dependency structure analysis, plus a routing overview. Pairing the skills with the MCP server lets an agent carry out a complete project risk workflow (for example, mcs_tool followed by contingency_tool and sensitivity_tool) from a natural-language request, without embedding an LLM in the package itself.

The MCP layer is strictly optional: every analytical function operates without any optional dependency. Only pra_mcp_server() requires ellmer, mcptools, and jsonlite.

# 8	Illustrative Case Study

This section demonstrates an integrated, end-to-end project risk analysis for the building_project dataset introduced in Section 2, progressing through uncertainty quantification, risk-driver ranking, performance monitoring, completion forecasting, Bayesian risk updating, dependency structure analysis, and network cost propagation in a single R session. The workflow reuses objects built in the preceding sections (for example the closed-form task moments, the fitted learning curve, and the probabilistic network), illustrating how the modules compose within one analysis.

## 8.1	Step 1: Characterize Task Uncertainty

Combine the rapid analytical estimate from the Second Moment Method—reusing the closed-form triangular moments task_means and task_vars from Section 2 with the dataset correlation matrix—with the full simulated distribution from Monte Carlo simulation:

bp <- building_project
set.seed(42)

smm_cs <- smm(task_means, task_vars, bp$cor_mat)   # analytic, correlated
sim     <- mcs(10000, bp$task_distributions)        # full distribution
res     <- contingency(sim, phigh = 0.80, pbase = 0.50)

cat("SMM total (correlated): mean", round(smm_cs$total_mean, 1),
    "SD", round(smm_cs$total_std, 2), "weeks\n")

## SMM total (correlated): mean 71.7 SD 6.59 weeks

cat("P50 schedule:", round(quantile(sim$total_distribution, 0.50), 1), "weeks\n")

## P50 schedule: 71.6 weeks

cat("P80 schedule:", round(quantile(sim$total_distribution, 0.80), 1), "weeks\n")

## P80 schedule: 75.6 weeks

cat("Contingency (P80-P50):", round(res, 2), "weeks\n")

## Contingency (P80-P50): 3.98 weeks

## 8.2	Step 2: Rank Risk Drivers

sensitivity() ranks the tasks by their share of total schedule variance, focusing mitigation on the dominant drivers:

drivers <- sensitivity(bp$task_distributions)
names(drivers) <- bp$task_names
print(round(sort(drivers, decreasing = TRUE), 3))

##               Structural Frame Mechanical/Electrical/Plumbing 
##                          0.304                          0.206 
##    Interior Fit-out & Finishes              Building Envelope 
##                          0.206                          0.133 
##  Site Preparation & Earthworks                    Foundations 
##                          0.076                          0.076

## 8.3	Step 3: Monitor Earned Value at Mid-Project

pv_cs <- pv(bp$bac, bp$schedule, bp$time_period)
ev_cs <- ev(bp$bac, bp$actual_per_complete)
ac_cs <- ac(bp$actual_costs, bp$time_period, cumulative = FALSE)

cat("SPI:", round(spi(ev_cs, pv_cs), 3),
    " CPI:", round(cpi(ev_cs, ac_cs), 3), "\n")

## SPI: 0.889  CPI: 0.986

cat("EAC (typical): $", format(round(eac(bp$bac,
    method = "typical", cpi = cpi(ev_cs, ac_cs))), big.mark = ","), "\n")

## EAC (typical): $ 8,625,000

## 8.4	Step 4: Forecast Completion

Reusing the logistic learning curve fit_log fitted in Section 4, project percent-complete at future weeks with confidence bounds:

preds_cs <- predict_sigmoidal(fit_log, seq(10, 12, by = 1),
                              "logistic", conf_level = 0.95)
print(round(preds_cs, 1))

##    x pred  lwr  upr
## 1 10 84.3 78.2 90.3
## 2 11 84.3 78.2 90.4
## 3 12 84.3 78.2 90.5

## 8.5	Step 5: Update Risk Probability After Site Inspection

prior_r <- risk_prob(bp$cause_probs, bp$risks_given_causes,
                     bp$risks_given_not_causes)
post_r  <- risk_post_prob(bp$cause_probs, bp$risks_given_causes,
                          bp$risks_given_not_causes, bp$observed_causes)
cat("Prior P(delay):", round(prior_r, 3),
    "-> Posterior P(delay):", round(post_r, 3), "\n")

## Prior P(delay): 0.578 -> Posterior P(delay): 0.797

## 8.6	Step 6: Identify Coupled Tasks via DSM

g_cs <- grandparent_dsm(bp$resource_task, bp$risk_resource)
plot(g_cs)

Figure 8.1: Grandparent DSM for the case-study project, showing which task pairs share the most risk exposure through common resources.

The Grandparent DSM reveals which task pairs share risk exposure through common resources, informing targeted contingency allocation and resource decoupling decisions.

## 8.7	Step 7: Propagate Cost Through the Network

Finally, use the probabilistic network net from Section 6 to propagate cost uncertainty to the project total, then condition on the observation that Risk-2 (Technical Complexity) did not occur:

cat("Prior mean project cost: $",
    format(round(mean(sim_net$I)), big.mark = ","), "\n")

## Prior mean project cost: $ 113,612

cat("Prior P80 project cost:  $",
    format(round(quantile(sim_net$I, 0.80)), big.mark = ","), "\n")

## Prior P80 project cost:  $ 135,543

cat("Posterior mean (Risk-2 = 0): $",
    format(round(mean(learn_net$I)), big.mark = ","), "\n")

## Posterior mean (Risk-2 = 0): $ 95,729

Conditioning on the resolved risk lowers the expected project cost, closing the loop from uncertainty characterization to evidence-based updating.

# 9	Summary

PRA is a CRAN-available R package whose primary contribution is being the first of its kind to unify the foundational methods of quantitative project risk analysis in a single, open-source framework of ten integrated analytical modules: SMM, MCS, contingency analysis, sensitivity analysis, EVM (11 metrics), Bayesian risk inference and updating, cost risk distributions, sigmoidal learning curves, correlation matrix construction, and design structure matrices. As a secondary contribution, an experimental eleventh module delivers the first software implementation of the causal-network and probabilistic-network methods for project risk developed in Govan (2014) and Govan and Damnjanovic (2016, 2020), with forward simulation and Bayesian conditioning.

As a third contribution, version 0.5.0 exposes every analytical function as a tool over the Model Context Protocol, complemented by a bundled set of Agent Skills, so that LLM agents can drive the package without any embedded model—the first project risk analysis package to do so. All exported functions adhere to rOpenSci SRR standards, with a test suite verifying correctness, edge-case handling, and numerical stability across three operating systems. The package is licensed under MIT and the source is available at https://github.com/paulgovan/PRA; documentation and a companion online book are at https://paulgovan.github.io/PRA/.

## 9.1	Limitations and Future Work

Several limitations apply. First, PRA currently propagates uncertainty at the task level and does not yet model schedule logic—critical path, activity precedence, and resource leveling. Full schedule-network risk analysis, in which schedule Monte Carlo runs over an activity-precedence network, such as Program Evaluation and Review Technique / Critical Path Method (PERT/CPM) to identify the critical path and criticality indices under uncertainty, is a planned future direction that would extend PRA from task-level to network-level schedule risk. Second, mcs() induces task correlation by applying a Cholesky factor to the sampled values, which reproduces the target rank correlation but distorts the marginal means; the examples in this article therefore treat tasks as independent for Monte Carlo simulation and use smm(), which handles correlation analytically, when correlation matters. A copula-based implementation that preserves the marginals is planned. Third, the probabilistic network module is experimental: the API may change and no convergence diagnostics are provided for the Monte Carlo estimators. Fourth, the package currently accepts data as R vectors and lists.  Direct import from project management file formats (Microsoft Project, Primavera P6, CSV exports from Jira or Asana) is not supported and is planned for a future release.

# Computational details

The results in this article were produced using R (R Core Team 2024) with the PRA package (version 0.5.0) and its hard dependencies mc2d (Pouillot and Delignette-Muller 2010) and minpack.lm (Elzhov et al. 2016). The optional Model Context Protocol server additionally uses ellmer (Wickham et al. 2025), mcptools, and jsonlite. R itself and all packages used are available from the CRAN at https://CRAN.R-project.org/. A random seed of 42 is set at the start of the session so that the simulation output is reproducible.

# References

Anthropic. 2024. Model Context Protocol. https://modelcontextprotocol.io.

Benjamin, Jack R., and C. Allin Cornell. 2000. Probability, Statistics, and Decision for Civil Engineers. Dover Publications.

Browning, Tyson R. 2001. “Applying the Design Structure Matrix to System Decomposition and Integration Problems: A Review and New Directions.” IEEE Transactions on Engineering Management 48 (3): 292–306. https://doi.org/10.1109/17.946528.

Bürkner, Paul-Christian. 2017. “: An  Package for Bayesian Multilevel Models Using .” Journal of Statistical Software 80 (1): 1–28. https://doi.org/10.18637/jss.v080.i01.

Damnjanovic, Ivan, and Kenneth Reinschmidt. 2020. Data Analytics for Engineering and Construction Project Risk Management. Springer. https://doi.org/10.1007/978-3-030-14251-3.

Elzhov, Timur V., Katharine M. Mullen, Andrej-Nikolai Spiess, and Ben Bolker. 2016. Minpack.lm: R Interface to the Levenberg-Marquardt Nonlinear Least-Squares Algorithm Found in MINPACK. https://CRAN.R-project.org/package=minpack.lm.

Fleming, Quentin W., and Joel M. Koppelman. 2010. Earned Value Project Management. 4th ed. Project Management Institute.

Govan, Paul. 2014. “A Resource-Based View on Project Risk Management.” PhD thesis, The University of Texas at Austin.

Govan, Paul, and Ivan Damnjanovic. 2016. “The Resource-Based View on Project Risk Management.” Journal of Construction Engineering and Management 142 (9): 04016034. https://doi.org/10.1061/(ASCE)CO.1943-7862.0001157.

Iooss, Bertrand, Sébastien Da Veiga, Alexandre Janon, and Gilles Pujol. 2024. Sensitivity: Global Sensitivity Analysis of Model Outputs. https://CRAN.R-project.org/package=sensitivity.

Pearl, Judea. 2009. Causality: Models, Reasoning, and Inference. 2nd ed. Cambridge University Press.

Pouillot, Regis, and Marie-Laure Delignette-Muller. 2010. “Evaluating Variability and Uncertainty in Microbial Quantitative Risk Assessment Using Two r Packages.” International Journal of Food Microbiology 142 (3): 330–40. https://doi.org/10.1016/j.ijfoodmicro.2010.07.011.

Project Management Institute. 2021. A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th ed. Project Management Institute.

R Core Team. 2024. : A Language and Environment for Statistical Computing. R Foundation for Statistical Computing. https://www.R-project.org/.

rOpenSci Statistical Software Peer Review. 2021. Statistical Software Peer Review: Standards and Guidelines. https://stats-devguide.ropensci.org.

Stan Development Team. 2024. : The  Interface to . https://mc-stan.org/.

Steward, D. V. 1981. Systems Analysis and Management: Structure, Strategy and Design. Petrocelli Books.

Vose, David. 2008. Risk Analysis: A Quantitative Guide. 3rd ed. Wiley.

Wickham, Hadley et al. 2025. Ellmer: Chat with Large Language Models. https://ellmer.tidyverse.org.