# An AI Agent Framework for Quantitative Project Risk Analysis: Integrating Large Language Models with Validated Probabilistic Tools

2026-05-23

Abstract

Quantitative methods for project risk analysis — including Monte Carlo simulation, Earned Value Management, and Bayesian inference — are well-established in theory but underutilized in practice due to their technical complexity and fragmented tooling. Large language model (LLM) agents capable of calling domain-validated code functions offer a promising path toward closing this gap. This paper presents an AI agent framework, implemented as the open-source R package PRA, that exposes a validated suite of project risk analysis functions as tools callable by LLMs through a three-mode routing architecture: deterministic slash commands for immediate reproducible results, LLM tool-calling for flexible natural-language queries, and Retrieval-Augmented Generation (RAG) for conceptual questions grounded in domain literature. We evaluate the framework across 25 scenarios in three tiers of complexity using the llama3.2 model (3.2B parameters, local inference). With RAG enabled, the agent achieves 72.0% overall tool-selection accuracy (87.5% on single-tool, 55.6% on multi-tool chains, 75.0% on open-ended queries), compared to 68.0% without RAG. RAG substantially improves multi-tool chain accuracy (+11.1%) and open-ended response quality (+12.5%) at the cost of reduced single-tool precision (−12.5%), a trade-off fully mitigated by the slash command interface for deterministic workflows. The framework is available on CRAN, supports the Model Context Protocol for interoperability with Claude, Claude Code, and other AI clients, and runs fully offline via Ollama — requiring no cloud API keys or data transmission.

# 1. Introduction

Quantitative risk analysis is central to sound project management. Methods such as Monte Carlo simulation (MCS), Earned Value Management (EVM), and Bayesian risk inference provide project managers and cost engineers with principled tools for quantifying schedule uncertainty, diagnosing cost overruns, and updating risk beliefs as projects evolve(1–3). Yet surveys of project management practice consistently show that quantitative risk techniques remain underutilized, with most organizations relying on qualitative risk registers rather than probabilistic analysis(1). The barriers are well understood: these methods require statistical expertise to apply correctly, their implementations are scattered across commercial tools (Palisade @RISK, Primavera Risk Analysis) that are expensive and not reproducible, and practitioners often lack the time or training to connect the right tool to each type of problem.

Large language models (LLMs) have emerged as a potentially transformative interface for domain expertise. Through tool calling — the ability to invoke external functions in response to natural language queries — LLMs can act as intelligent intermediaries that translate a practitioner’s intent into a validated computational pipeline(4). Rather than requiring users to know which function to call and how to parameterize it, the agent selects and invokes the appropriate tool automatically. This capability has been demonstrated in general software engineering contexts, but its application to specialized engineering analysis domains — particularly project risk — remains nascent.

Retrieval-Augmented Generation (RAG) complements tool calling by grounding agent responses in domain-specific knowledge(5). For conceptual queries (“what is the difference between SPI and CPI?” or “how does Bayesian inference apply to cost risk?”), RAG retrieves relevant passages from a curated knowledge base and presents them as context for the LLM’s response, reducing hallucination and improving source attribution(6,7). Together, tool calling and RAG address the two primary failure modes of general-purpose LLMs in engineering contexts: incorrect tool selection or parameterization, and fabrication of quantitative claims.

This paper presents a novel AI agent framework for quantitative project risk analysis, implemented as part of the open-source R package PRA(8) and available on the Comprehensive R Archive Network (CRAN). The framework makes four contributions:

- A three-mode routing architecture — deterministic slash commands, LLM tool-calling, and RAG — that accommodates different user workflows and reliability requirements within a single interface.

- A validated analytical tool layer comprising 14 LLM-callable tools and 9 deterministic commands, wrapping a peer-reviewed suite of project risk analysis functions that cover MCS, SMM, EVM, contingency analysis, sensitivity analysis, Bayesian inference, learning curves, and dependency structure matrices.

- Model Context Protocol (MCP) integration via the mcptools package(9), enabling PRA tools to be called natively from Claude, Claude Code, and any MCP-compatible AI client without additional configuration.

- A systematic evaluation of agent performance across 25 scenarios in three tiers of complexity, providing the first published benchmark of an LLM agent for quantitative project risk analysis.

The remainder of the paper is organized as follows. Section 2 reviews the relevant background. Section 3 describes the framework architecture. Section 4 presents the evaluation methodology and results. Section 5 discusses implications and limitations. Section 6 concludes.

# 2. Background

## 2.1 Quantitative Project Risk Methods

Project risk analysis encompasses a range of techniques for quantifying uncertainty in schedule, cost, and performance. Monte Carlo simulation samples from probability distributions assigned to individual tasks and aggregates them over many iterations to produce a project-level distribution from which contingency reserves and risk-adjusted completion probabilities can be derived(2). The Second Moment Method (SMM) provides a computationally cheaper analytical approximation, propagating means and variances through the task network without simulation(1). Earned Value Management tracks project performance against a baseline cost and schedule plan using a set of standardized metrics — Cost Performance Index (CPI), Schedule Performance Index (SPI), Estimate at Completion (EAC), and others — defined in the ANSI/EIA-748 standard(3). Bayesian risk inference applies the law of total probability and Bayes’ theorem to estimate and update risk event probabilities as observations arrive(10). Design Structure Matrices (DSM) model task coupling and risk propagation in complex project networks(11).

Despite their theoretical grounding, these methods see limited practical adoption. Each requires a different data format, a different software tool, and a different conceptual model. Commercial tools such as Palisade @RISK and Oracle Primavera Risk Analysis cover subsets of this space but are expensive, proprietary, and not amenable to reproducible research workflows. The PRA R package(8) was developed to consolidate these methods in a single, open-source, peer-reviewed implementation, but even a well-designed programmatic interface requires users to understand which function addresses their question and how to format its inputs.

## 2.2 LLM Tool Calling

The ability for LLMs to invoke external functions — variously called tool calling, function calling, or code execution — has emerged as a key capability for building AI agents that act on the world rather than only describing it(4). When a user’s query contains structured data that can be processed by a validated function, the LLM selects the appropriate tool from a registered set, constructs the call arguments, invokes the function, and incorporates the result into its response. This paradigm separates the natural language understanding task (which LLMs perform well) from the computation task (which validated code performs reliably), combining the strengths of both.

The ellmer R package(12) provides a unified interface for LLM tool calling in R, supporting Ollama local models, OpenAI, Anthropic, and other backends through a consistent tool() registration API. Tools defined with ellmer::tool() can be registered on a chat object and reused across conversational turns, making them a natural fit for the PRA agent framework.

## 2.3 Retrieval-Augmented Generation

Retrieval-Augmented Generation augments LLM responses with passages retrieved from an external knowledge base, enabling models to answer domain-specific questions without requiring that knowledge to be encoded in model weights(5). A retrieval system indexes a corpus of documents as vector embeddings; at query time, the most semantically similar chunks are retrieved and inserted into the LLM’s context window as grounding evidence. Reviews of RAG systems find that hybrid retrieval — combining dense vector similarity search with sparse keyword matching (BM25) — generally outperforms either approach alone, particularly for domain-specific terminology(6).

For engineering decision support, the transparency and source attribution properties of RAG are especially important.(7) find that domain experts are more willing to trust AI-generated responses when retrieved source passages are visible, allowing them to verify claims against primary literature. In the project risk context, where practitioners may need to defend their analyses to stakeholders, the ability to cite a specific EVM standard or simulation methodology is a meaningful quality criterion.

## 2.4 AI-Assisted Engineering Decision Support

AI-assisted decision support has been explored across a range of engineering risk contexts.(13) demonstrate that LLMs can support principled decision making under uncertainty by combining probabilistic reasoning with chain-of-thought prompting.(14) show that LLM integration accelerates Failure Mode and Effects Analysis (FMEA) — a structured risk identification technique closely related to project risk assessment — while maintaining accuracy comparable to expert analysts.(15) combine RAG with LLMs to provide automated safety risk guidance, demonstrating that domain-grounded generation substantially outperforms base LLM responses on compliance-critical queries.

A common theme across these works is that LLM agents are most effective when tightly coupled with validated domain tools or knowledge sources rather than relying on the model’s parametric knowledge alone. The PRA agent framework adopts this design principle explicitly: the LLM is responsible for understanding user intent and selecting tools, while all quantitative computation is delegated to validated R functions.

# 3. Framework Design

## 3.1 Architecture Overview

The PRA agent framework is organized in three layers (Figure 1):

- Interface layer: The user interacts through one of three surfaces — a programmatic R chat object (pra_chat()), a Shiny web application (pra_app()), or any MCP-compatible AI client via pra_mcp_server().

- Routing layer: User input is classified into one of three modes — command, tool, or rag — by a heuristic classifier that examines the input for slash prefixes, numerical data patterns, and conceptual question markers.

- Execution layer: Classified inputs are dispatched to the appropriate handler: the command registry (deterministic), the LLM tool-calling loop (probabilistic), or the RAG retrieval pipeline (knowledge-grounded).

This architecture separates concerns cleanly: reliability-critical workflows use the command path, exploratory analysis uses the tool-calling path, and conceptual learning uses the RAG path. A single entry point handles all three modes, so users do not need to choose a different application for each workflow.

Figure 1. Three-layer architecture of the PRA AI agent framework. User input enters through the interface layer, is classified by the routing layer into one of three modes, and dispatched to the appropriate execution handler.

## 3.2 Input Routing

The routing classifier (route_input()) operates as follows. If the input begins with a forward slash, it is classified as a command and dispatched to the command registry without involving the LLM. Otherwise, the input is scanned for numerical patterns: distribution specifications (e.g., normal(10, 2)), JSON arrays, monetary amounts ($500,000), EVM keywords (BAC, schedule), and structured parameter assignments (mean=, costs=). If any pattern matches, the input is classified as a tool call. If no numerical patterns are found, the input is classified as rag and the knowledge base is queried for relevant context.

The LLM is involved in both the tool and rag modes but plays different roles. In tool mode, the system prompt encodes tool-selection heuristics — for example, “if the user provides distribution specifications, call mcs_tool, then contingency_tool and sensitivity_tool” — and the LLM selects and invokes the appropriate tools. In rag mode, retrieved passages are inserted into the context window and the LLM synthesizes a response with source attribution.

The classification heuristic is intentionally lightweight: it trades recall for precision, occasionally routing tool-call queries to RAG when numerical patterns are absent, but never routing conceptual questions through the tool-calling path (which would produce spurious function invocations). Users can always override classification by using a slash command directly.

## 3.3 Analytical Tool Layer

The tool layer comprises 14 ellmer::tool() definitions, each wrapping one or more PRA analytical functions. Table 1 summarizes the tools.

Table 1. LLM-callable tools in the PRA agent registry.

| Tool | R Function(s) | Description |
| --- | --- | --- |
| mcs_tool | mcs() | Monte Carlo simulation with task distributions and correlations |
| smm_tool | smm() | Second Moment Method analytical project estimate |
| contingency_tool | contingency() | Contingency reserve derived from simulation percentile |
| sensitivity_tool | sensitivity() | Variance contribution by task (tornado chart) |
| evm_analysis_tool | EVM suite | Full ANSI/EIA-748 dashboard: 11 EVM metrics |
| risk_prob_tool | risk_prob() | Bayesian prior risk probability from root causes |
| risk_post_prob_tool | risk_post_prob() | Bayesian posterior probability after observed evidence |
| cost_pdf_tool | cost_pdf() | Prior cost risk distribution (Beta-Binomial) |
| cost_post_pdf_tool | cost_post_pdf() | Posterior cost distribution after observations |
| fit_and_predict_sigmoidal_tool | fit_sigmoidal() + predict_sigmoidal() | Sigmoidal learning curve fit and completion forecast |
| parent_dsm_tool | parent_dsm() | Resource-task dependency matrix (parent DSM) |
| grandparent_dsm_tool | grandparent_dsm() | Risk-resource-task dependency matrix (grandparent DSM) |

All tool inputs are passed as JSON strings (matching the format LLMs naturally produce), and a fault-tolerant JSON parser (parse_json()) handles common LLM output artifacts such as smart quotes, trailing commas, and missing array brackets.

Tool outputs are designed for dual use: plain-text summaries are returned to the LLM for incorporation into conversational responses, while rich HTML outputs (inline charts and formatted tables) are rendered in the Shiny interface. Full simulation results (e.g., the 10,000-element distribution vector from mcs_tool) are stored in a package-level environment (.pra_agent_env) rather than returned verbatim, which keeps the LLM’s context window manageable and enables tool chaining — the contingency_tool and sensitivity_tool read from .pra_agent_env$last_mcs rather than requiring the user to re-specify the simulation.

In addition to the LLM-callable tools, nine deterministic slash commands (Table 2) provide the same analytical capabilities through a structured argument syntax that bypasses the LLM entirely. Commands use a bracket-aware argument parser (parse_command_args()) that handles nested JSON values in command arguments without regex fragility. The commands produce identical numerical results to the tools but execute in milliseconds and guarantee reproducibility.

Table 2. Deterministic slash commands. Each command executes the corresponding analytical function directly without LLM involvement.

| Command | Equivalent Tool | Example Syntax |
| --- | --- | --- |
| /mcs | mcs_tool | /mcs n=10000 tasks=[{“type”:“normal”,“mean”:10,“sd”:2}] |
| /smm | smm_tool | /smm means=[10,15,20] vars=[4,9,16] |
| /contingency | contingency_tool | /contingency phigh=0.95 pbase=0.50 |
| /sensitivity | sensitivity_tool | /sensitivity tasks=[{“type”:“normal”,“mean”:10,“sd”:2}] |
| /evm | evm_analysis_tool | /evm bac=500000 schedule=[0.2,0.4,0.6,0.8,1.0] period=3 complete=0.55 costs=[90000,195000,310000] |
| /risk | risk_prob_tool | /risk causes=[0.3,0.2] given=[0.8,0.6] not_given=[0.2,0.4] |
| /risk_post | risk_post_prob_tool | /risk_post causes=[0.3,0.2] given=[0.8,0.6] not_given=[0.2,0.4] observed=[1,null] |
| /learning | fit_and_predict_sigmoidal_tool | /learning model=logistic x=[1,2,3,4,5,6,7,8] y=[2,8,25,50,72,88,95,98] |
| /dsm | parent_dsm_tool | /dsm matrix=[[1,1,0],[0,1,1],[0,0,1]] |

## 3.4 RAG Knowledge Layer

The knowledge base consists of six curated Markdown documents (~19 KB total) covering the core project risk analysis methods:

- mcs_methods.md — distribution selection, correlation, convergence criteria

- evm_standards.md — ANSI/EIA-748 metrics and EAC forecasting methods

- bayesian_risk.md — prior/posterior probability, Beta-Binomial model

- sensitivity_contingency.md — variance decomposition, reserve calculation

- learning_curves.md — logistic, Gompertz, and Pearl sigmoidal models

- pra_functions.md — comprehensive function reference

Documents are chunked using Markdown-aware splitting via ragnar::markdown_chunk() and stored in a DuckDB database through the ragnar package(16). At query time, retrieve_context() performs hybrid retrieval combining BM25 keyword matching and vector similarity search over 768-dimensional embeddings produced by the nomic-embed-text model running locally via Ollama(17). The top-3 chunks are returned with source filenames for attribution. The database is built on first use and cached locally, so subsequent calls operate from the cached store without re-embedding.

The knowledge base is user-extensible via add_documents(), which ingests additional .md or .txt files and rebuilds the index. This allows organizations to add project-specific risk registers, standards documents, or historical performance data as grounding context.

## 3.5 MCP Integration

The Model Context Protocol(18) defines a standard interface through which AI clients can discover and invoke external tools via JSON-RPC 2.0 over stdio or HTTP/SSE transports. The pra_mcp_server() function launches PRA as an MCP server, exposing the same 14 tools as the ellmer layer through this protocol:

pra_mcp_server()  # starts stdio MCP server

The implementation delegates to mcptools::mcp_server(tools = pra_tools())(9), reusing the existing ellmer::tool() definitions without duplication. Claude Code, Claude Desktop, and other MCP clients can connect by adding PRA to their MCP server configuration. A project-level .claude/mcp.json file is included in the package repository for zero- configuration Claude Code integration:

{
  "mcpServers": {
    "pra": {
      "command": "Rscript",
      "args": ["-e", "PRA::pra_mcp_server()"]
    }
  }
}

MCP integration decouples the PRA tool layer from the R-based agent orchestration: any MCP-compatible AI client gains access to validated project risk analysis functions without requiring R session management or Shiny.

## 3.6 Implementation

The framework is implemented as part of the PRA R package (v0.4.0), available on CRAN. The agent components span approximately 2,400 lines of R across three source files: R/chat.R (agent initialization, system prompt, MCP server), R/rag.R (knowledge base construction and retrieval), and R/tools.R (tool wrappers, command registry, and input router). Hard dependencies are limited to mc2d, minpack.lm, and stats; all AI components are in Suggests and loaded on demand.

By default, PRA uses locally running Ollama models(17) — specifically llama3.2 (3.2B parameters) for generation and nomic-embed-text (137M parameters) for embeddings. This design is deliberate: local inference preserves data privacy (no project data leaves the user’s machine), eliminates per-query API costs, and operates without network connectivity. Users who prefer higher accuracy for complex tool-calling scenarios can supply a pre-configured ellmer chat object using a cloud model (e.g., ellmer::chat_anthropic(model = "claude-opus-4-7")); the agent architecture is model-agnostic.

The Shiny application (pra_app()) provides a browser-based interface with streaming responses, inline visualizations from tool outputs, and example prompt chips that demonstrate all three input modes. It is launched with a single R call and requires no web server configuration.

# 4. Evaluation

## 4.1 Design

We evaluate the agent’s ability to correctly identify and invoke the appropriate analytical tools in response to user queries, using a benchmark of 25 scenarios spanning three tiers of complexity:

- Tier 1 — Single-tool (8 scenarios): Each scenario requires exactly one tool call with correctly specified parameters. Examples include “Run a Monte Carlo simulation with 10,000 iterations for a 3-task project with Normal(10,2), Triangular(5,10,15), and Uniform(8,12) distributions” and “Fit a logistic learning curve to this data: x = [1..8], y = [2,8,25,50,72,88,95,98].”

- Tier 2 — Multi-tool chain (9 scenarios): Each scenario requires two or more tool calls in sequence. Examples include MCS followed by contingency reserve calculation, full EVM analysis with forecast interpretation, and Bayesian prior computation followed by posterior updating with observed evidence.

- Tier 3 — Open-ended (8 scenarios): Conceptual queries that do not require tool calls but should be answered with domain-accurate content citing the knowledge base. Examples include “How do Bayesian risk methods differ from Monte Carlo simulation?” and “My project’s CPI is 0.85 and SPI is 0.92. Should I be concerned?”

Scoring follows a three-level rubric for Tiers 1 and 2: Correct (all expected tools called), Partial (some expected tools called), and Incorrect (no expected tools called). For Tier 3, responses are scored on keyword coverage: Correct if ≥50% of domain-relevant keywords appear, Partial if any keywords match, Incorrect otherwise. The evaluation framework is implemented using the vitals R package(19).

We test two configurations: llama3.2 with RAG enabled (the default) and llama3.2 with RAG disabled (ablation). The llama3.2 model (Meta, 3.2B parameters) was chosen as a representative small local model accessible to practitioners without GPU hardware. All inference runs locally via Ollama with a 16,384-token context window. Each configuration is run in a single trial.

## 4.2 Results

Table 3 summarizes the evaluation results.

Table 3. Tool-selection accuracy by configuration and tier.

| Configuration | Overall | Single-tool (n=8) | Multi-tool (n=9) | Open-ended (n=8) |
| --- | --- | --- | --- | --- |
| llama3.2 + RAG | 72.0% | 87.5% | 55.6% | 75.0% |
| llama3.2 (no RAG) | 68.0% | 100.0% | 44.4% | 62.5% |
| RAG delta | +4.0% | -12.5% | +11.1% | +12.5% |

With RAG enabled, the agent achieves 72.0% overall accuracy: 87.5% on single-tool scenarios, 55.6% on multi-tool chains, and 75.0% on open-ended queries. Without RAG, overall accuracy falls to 68.0%, with 100.0% on single-tool, 44.4% on multi-tool, and 62.5% on open-ended.

## 4.3 Discussion of Results

The RAG ablation reveals a clear pattern. RAG substantially improves performance on multi-tool chains (+11.1 percentage points) and open-ended conceptual queries (+12.5 pp), while reducing performance on single-tool scenarios (−12.5 pp). We interpret this as follows.

For multi-tool chains, the retrieved context about method sequences (e.g., the mcs_methods.md document describes the typical workflow of simulation → contingency → sensitivity) provides the LLM with planning context that improves its ability to construct the correct tool call sequence. For open-ended queries, the retrieved passages directly supply the domain content the model needs, reducing reliance on the model’s parametric knowledge and improving keyword coverage. For single-tool scenarios, however, the additional context appears to prime the model toward explanation over action: when a passage about Monte Carlo methods is retrieved alongside a query requesting a simulation, the model sometimes generates an explanatory response about the method rather than immediately calling mcs_tool.

This trade-off is practically mitigated by the slash command interface. Single-tool scenarios correspond precisely to the use case for which slash commands were designed: the user knows which computation they want and provides the data. Typing /mcs tasks=[...] guarantees correct tool invocation in zero latency with no LLM involvement. The 100% single-tool accuracy of the no-RAG configuration would be matched — and exceeded in speed and reliability — by the deterministic command path.

Multi-tool chain performance (55.6% with RAG) represents the most significant remaining limitation. Failures in this tier are predominantly attributable to the model omitting the second tool in a chain — for example, running MCS but not following through to contingency_tool — rather than calling the wrong tool. This suggests that multi-step planning is the principal challenge for a 3.2B parameter model at the task complexity level tested. We expect larger models (8B+) and cloud-hosted models (GPT-4o, Claude Opus) to show substantially higher accuracy on this tier, which we leave for future work.

# 5. Discussion

## 5.1 Implications for Risk Practice

The PRA agent framework lowers the barrier to quantitative risk analysis in two complementary ways. First, the natural language interface means practitioners no longer need to memorize function signatures or data formats: they can describe their project in plain language and let the agent select and invoke the appropriate analytical pipeline. Second, the slash command interface means practitioners who have learned a workflow can execute it instantly and reproducibly, without LLM latency or variability.

These two affordances serve different user profiles. A risk analyst encountering a new project type benefits from the exploratory, conversational interface; an experienced analyst running weekly EVM updates benefits from the deterministic /evm command. The three-mode architecture accommodates both within a single tool.

## 5.2 Comparison to Prior Approaches

Compared to commercial tools (Palisade @RISK, Primavera Risk Analysis), PRA offers full reproducibility through open-source R, no licensing cost, and programmatic integration with the broader R statistical ecosystem. The AI agent layer adds a natural language interface that these tools lack.

Compared to general-purpose LLMs (GPT-4, Claude, Gemini), PRA offers validated quantitative computation. General-purpose LLMs can reason about project risk in natural language but cannot reliably perform numerical simulation, EVM calculation, or Bayesian updating; when they attempt to, they frequently produce plausible-looking but incorrect numbers(13). By routing computation to validated R functions, PRA eliminates this failure mode.

Compared to general R agent frameworks, PRA provides domain-specific tool definitions, a curated knowledge base, and a Shiny interface optimized for project risk workflows. The MCP integration additionally enables users to call PRA functions from Claude Code and other AI clients without writing any R code.

## 5.3 Design Trade-offs

The choice to use local Ollama models by default prioritizes privacy and accessibility over accuracy. The llama3.2 (3.2B) model achieves 72.0% overall accuracy — adequate for exploratory use and reliable for single-tool scenarios, but below what larger models would likely achieve for complex multi-tool chains. Organizations with cloud access can substitute a more capable model; the architecture is model-agnostic. A systematic model comparison benchmark is left for future work.

The hybrid BM25 + vector similarity RAG retrieval performs well on the domain-specific terminology in the knowledge base, but the current knowledge corpus is intentionally small (~19 KB across six documents). Expanding the corpus with project-specific standards, historical project data, or additional risk frameworks would increase retrieval quality but also increase the risk of retrieval noise degrading response coherence.

## 5.4 Generalizability

The three-mode routing architecture — deterministic commands, LLM tool-calling, and RAG — is not specific to project risk analysis. Any domain that has (1) a set of validated computational functions in R and (2) a corpus of domain knowledge in text form can adopt the same architecture. The ellmer + ragnar + mcptools stack used here provides a reusable implementation pattern.

## 5.5 Limitations and Future Work

Several limitations of the current work point toward future research directions.

Evaluation scope. The 25-scenario benchmark uses a single model (llama3.2) in a single trial. Multi-trial evaluation with confidence intervals, and systematic comparison across model families and sizes (e.g., llama3.1 8B, Qwen2.5, GPT-4o, Claude Opus), would provide a more complete picture of the accuracy-model-size trade-off.

Scoring methodology. The tool-selection accuracy metric captures whether the correct functions were called, but not whether the parameters were correctly specified or whether the final answer was numerically correct. A complementary end-to-end correctness metric — comparing tool output values to reference solutions — would provide a more rigorous evaluation.

Human baseline. The evaluation does not include a human-baseline condition. Comparing agent performance to that of domain experts operating the same tools manually would provide the most meaningful measure of practical utility.

Multi-turn conversations. The current evaluation tests single-turn performance. Real project risk assessments typically involve iterative refinement — running a simulation, examining the results, adjusting assumptions, re-running. Multi-turn benchmark design is an important next step.

Data integration. Future versions could integrate with project management data sources (Microsoft Project, Primavera, ERP systems) to ingest schedule and cost actuals automatically, removing the data-entry burden that is one of the main practical barriers to quantitative risk analysis.

# 6. Conclusion

This paper presented an AI agent framework for quantitative project risk analysis that integrates large language model tool-calling with a validated suite of probabilistic analysis functions. The framework’s three-mode routing architecture — deterministic slash commands, LLM tool-calling, and Retrieval-Augmented Generation — serves a range of user workflows: from instant reproducible computation for experienced analysts to exploratory natural language interaction for practitioners new to quantitative methods.

Systematic evaluation across 25 scenarios demonstrates 72.0% tool-selection accuracy with a small local model (llama3.2, 3.2B parameters), with RAG providing meaningful improvements for multi-tool chains (+11.1%) and open-ended conceptual queries (+12.5%). The Model Context Protocol integration extends the framework’s reach to Claude, Claude Code, and other MCP-compatible AI clients, enabling quantitative project risk analysis from any LLM interface.

The framework is fully open source, available on CRAN as the PRA package (version 0.4.0), and operates entirely locally with no cloud API dependencies. By combining the accessibility of natural language with the reliability of validated quantitative tools, it offers a practical path toward broader adoption of evidence-based quantitative risk analysis in project management.

# Acknowledgments

The author thanks the developers of the ellmer, ragnar, mcptools, and vitals R packages, whose work provided the foundational infrastructure for this framework.

# References

1. 	Damnjanovic I, Reinschmidt K. Data Analytics for Engineering and Construction Project Risk Management. Cham, Switzerland: Springer, 2020.

2. 	Vose D. Risk Analysis: A Quantitative Guide. 3rd ed. Chichester: Wiley, 2008.

3. 	Fleming QW, Koppelman JM. Earned Value Project Management. 4th ed. Newtown Square, PA: Project Management Institute, 2010.

4. 	Patil SG, Zhang T, Wang X, Gonzalez JE. Gorilla: Large language model connected with massive APIs. arXiv preprint arXiv:2305.15334, 2023.

5. 	Lewis P, Perez E, Piktus A, Petroni F, Karpukhin V, Goyal N, Küttler H, Lewis M, Yih W, Rocktäschel T, Riedel S, Kiela D. Retrieval-augmented generation for knowledge-intensive NLP tasks. Pp. 9459–9474 in Advances in Neural Information Processing Systems. Vol 33. 2020.

6. 	Gao Y, Xiong Y, Gao X, Jia K, Pan J, Bi Y, Dai Y, Sun J, Wang M, Wang H. Retrieval-augmented generation for large language models: A survey. arXiv preprint arXiv:2312.10997, 2024.

7. 	Jhaver S et al. Exploring trust and transparency in retrieval-augmented generation for domain experts. in Extended Abstracts of the CHI Conference on Human Factors in Computing Systems. 2025.

8. 	Govan P. PRA: Project Risk Analysis., 2026.

9. 	Posit PBC. Mcptools: Model Context Protocol Tools for R., 2025.

10. 	Gelman A, Carlin JB, Stern HS, Dunson DB, Vehtari A, Rubin DB. Bayesian Data Analysis. 3rd ed. Boca Raton, FL: CRC Press, 2013.

11. 	Browning TR. Applying the design structure matrix to system decomposition and integration problems: A review and new directions. IEEE Transactions on Engineering Management, 2001; 48(3):292–306.

12. 	Wickham H et al. Ellmer: Chat with Large Language Models., 2025.

13. 	Liu O, Shi D, Haimes J, Yang D, Webb C, Mao S, Kim S, Wang K. DeLLMa: Decision making under uncertainty with large language models. arXiv preprint arXiv:2402.02392, 2024.

14. 	Spreafico C, Russo D. AI-driven FMEA: Integration of large language models for faster and more accurate risk analysis. Design Science, 2025; 11.

15. 	Zhang W et al. Automated safety risk management guidance enhanced by retrieval-augmented large language model. Safety Science, 2025.

16. 	Posit PBC. Ragnar: Retrieval-Augmented Generation for R., 2025.

17. 	Ollama. Ollama: Get up and running with large language models locally. 2023.

18. 	Anthropic. Model context protocol. 2024.

19. 	Tidyverse team. Vitals: Evaluate LLM Performance., 2025.